## HLPS Action Plan
"Aiming High Together"
Hilton Lane Primary School Governing Board Action Plan 2022-2025
Background: As a result of whole governing body training and completing the self-evaluation audit document the governors decided to write an Action Plan. The audit will be revisited continuously through 2022/25 to measure progress, and an updated version published in 2023/2024 academic year
Overarching areas of Focus- Objective 1 - To significantly improve outcomes in English -reading/phonics and writing - Objective 2 - To significantly improve outcomes for SEND children across the curriculum Objective 3 - To further develop the use of assessment across the curriculum to monitor and challenge progress - Objective 4 - To significantly improve attendance (both overall and persistence)
Key Objectives for Improvement: 1) Organisation and Teamwork 2) Strategic Leadership 3) Support and Challenge 4) Accountability
Evaluation: Each task of the Governing Body is evaluated regularly using a 'RAG' status (shown in the last column). A green ratings means that tasks have been adequately completed, amber means it is in progress and red means that the task has not yet been commenced.
Key Tasks | Who/How | Timescale | Cost | Success Criteria | Evaluation - Last updated January 2024
ORGANISATION AND TEAMWORK To Improve Induction for New Governors
Recruit new Governor's to GB and upskill current Board- Parent Governor and Co-opted Governor, to include Financial Skills base. | Mentors to be introduced to new governors at their first attendance of the FGB meeting | Summer Term 23 | None | 1) Recruitment of new Governors 2) Retention of new governors for a full term | x2 vacancies on the Board currently, x3 elections for parent governor not be successful. Following LA advice, Summer term attempt recruit a Grandparent as Gov. Chair to look at recruitment website for co-opted Governor. Following skills matrix review need to recruit Gov with Financial experience
Governors need to be fully aware of their role and responsibilities and how their skills can support the governing body | Attendance at relevant induction and training for specific roles/committees | Audit to be conducted annually at beginning of each academic year | None (Training SLA covers all governing board training needs) | 1) A skills audit for the governing body that identifies a balance for the whole board, with plans effectively implemented to plug any skills gap through training. 2) Training courses attended are reported back to the FGB to share experiences and good practice | Skills audit completed annually and last completed in Jan 2022. Training is continually undertaken by the Governors, both individually, and as a full governing body. The Chair also acts as Training & Development Governor, ensuring training is taking place and is shared.
Monitor training and CPD of all governors to ensure up to date training in key areas and also develop members areas of interest | Chair to co-ordinate training for Governors | Ongoing at each FGB and sub committee | None (Training SLA covers all governing board training needs) | 1) Annual skills audit to be undertaken by Chair to identify up-skilling of governors | School purchase training SLA and also uses the National College. SG and PREVENT training mandate for all Governors and has been completed. Central record kept. Safer recruitment identified for non-teaching staff. Areas of focus reviewed at each GB and also at ad hoc meetings the board hold term to look at their development and plan. Last meeting 10.01.23. Next Scheduled 17.04.23
Succession Planning | Develop an ongoing matrix of roles and responsibilities preparing for changes over time and of needs | Ongoing considerations | None | 1) If a governor steps down from the board, ensure another has the knowledge and skills to succeed the outgoing governor, 2) Current member confident to chair and challenge as required. | Key task of 22/23 year is to devolve from Chair. New VC in post following resignation of previous encumberment. Committee chair also reallocated based on skills matrix for 22/23 AY and to upskill members. National College training suggested around leadership and chairing
Key Tasks | Who/How | Timescale | Cost | Success Criteria | Evaluation
STRATEGIC LEADERSHIP: To improve governance
To continue to develop monitoring and evaluation processes | Link governor visits to be recorded via writing of reports | Ongoing. At least one per Governor, per term | None | 1) Link governor's reports to be uploaded to Shared Governors folder 2) Link governors to be established at the first FGB meeting of the year | Full scheduled of visits planned by Governors for 22/23 AY, with one visit per terms, focusing in linked areas, including link to SIP and areas of focus. Report written after each visit and reviewed as item of FGB. Chair meets in school with HT monthly and conducts walkaround.
Each governor to visit school during the school day for a ‘Learning Walk’ at least once per term | All governors. A visit diary has been established to record all visits to the school | Ongoing, at least one visit per term, per non-staff governor. | None | 1) Learning Walk visits and reports for the following: one per year group and one per subject as a minimum. 2) Reports to be uploaded to the governors Shared folder. | Learning walk held in Jan 2023 and governors are invited to further learning walks throughout the school year. Governors are also invited to attend school events and activities to ensure they see the school in action and are visible to staff, parents and pupils. Chair visits at least once per month and conducts walkaround.
Governors to work together on school visits and work collaboratively on reports | All Governors | Ongoing. | None | Team working skills seen to improve knowledge and skills for both buddies, and giving feedback to board | In 22/23 AY GB has met termly outside of formal meeting to focus on development areas and priorities. This needs to deepen. Next meeting 18/04 17:00.
Develop a written vision and mission statement for the school to be published | All Governors | Summer Term 23 | None | 1) Publish a written vision linking to school aims and SIP goals | FGB meet 10.01.23 to draft a vision. Meeting scheduled for 18.04.23 to review and finalise.
Governors to use the Ofsted criteria for good against Leadership and Management as a training tool | All governors. Ongoing | Ongoing | None | 1) Ensure Ofsted criteria set out in Education Inspection Framework is read, understood and used in visits and reports | This is being monitored to ensure Ofsted criteria are embedded into the governor's ways of working.
Key Tasks | Who/How | Timescale | Cost | Success Criteria | Evaluation
SUPPORT AND CHALLENGE: To improve governance
To increase governor visits to the school in a planned and organised way to ensure feedback at FGB meeting and adding to the school website | All governors | Ongoing | None | 1) Staff report there is visibility of governors within the school. 2) Senior leadership and staff feel supported and challenged in an open and constructive manner. | Governors are encouraged to visit the school regularly. This continues to be monitored.
Improve the feedback to governors regarding the impact of staff training and development | More detail and impact in HT report. Staff to feedback as appropriate | Half-termly | None | 1) Improvements in communication to the GB on staff CPD | HT report includes information on the continuing professional development of staff.
Governors to join in on celebrations of success for staff and pupil achievements where appropriate | All governors, attendance at assemblies | Ongoing and as appropriate | None | 1) Staff and pupil morale and feeling of recognition from the governing board. | FGB will review the appropriateness and effectiveness of this type of engagement
Key Tasks | Who/How | Timescale | Cost | Success Criteria | Evaluation
ACCOUNTABILITY: To improve governance and the awareness of governors re. their accountability
The Governing Board will hold the Senior Leadership Team to account for all aspects of the school’s performance. | All governors - by reviewing, challenging and supporting the SLT’s mechanisms for monitoring performance of staff and pupils | At every FGB meeting and committee meetings | None | 1) Maintaining the high performance achieved in all areas that are monitored. 2) Rapid intervention plans are formulated and implemented in areas that are at risk of not meeting expectations | Assessed at each meeting and to be formally reviewed at the end of the school year. Governors ask good, strategic questions and training is encouraged to support this.
Support new Headteacher in role | All Governors | Ongoing | Nona | 1) HT feels support and constructively challenged in new post | HT new to post in 22/23 academic year. Ensure full support. Regular calls and meets with Chair on planned and ad-hoc basis as issues arise. Appraisal has taken place. Interim reviewed booked for 25.04.23.
Governors will ask questions of the headteacher and senior leaders at each meeting and these will be minute | All governors. School Governance Profession to minute the FGB meetings and SMB for committee | At every FGB meeting and committee meetings | None | 1) Thoroughly evidenced minutes for each of the FGB and committee meetings | Questioning of senior leaders has improved and continues to be an area of growth
Regularly monitor pupil progress. Monitor the impact of pupil premium on the progress of vulnerable groups | School Effectiveness Committee responsibility - through the review of performance data. | At every School Effectiveness Committee meeting | None | 1) The gap between vulnerable groups and other pupil groups will be narrowed 2) Senior leaders feel supported and pupil outcomes for vulnerable groups improved | Pupil Premium Governor specifically focuses on the impact of the pupil premium. Full Governing Body and Curriculum Committee monitor any attainment gaps and actions being taken to address it.
Actively support and promote British values within the school and monitor the Prevent agenda, | All governors: Safeguarding and Prevent link governor | Ongoing | None | 1) Governors and staff are confident the pupils have an understanding of the rule of law, democracy, mutual tolerance and respect for different faiths (or no faith), individual liberty appropriate to their age and level of development. 2) Pupils feel they are in an open and supportive environment. | Governors continually review this to ensure it is embedded in the curriculum and every day school life.